## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Risk Register
| Table 1 | Risk Register
Scale
| Table 1 | Scale

## Risk Register
FINANCIAL ANALYSIS RISK REGISTER
RISK DESCRIPTION | IMPACT DESCRIPTION | IMPACT LEVEL | PROBABILITY LEVEL | PRIORITY LEVEL | MITIGATION NOTES | OWNER | KEY
Give a brief summary of the risk. | What will happen if the risk is not mitigated or eliminated? | Rate 1 (LOW) to 5 (HIGH) | Rate 1 (LOW) to 5 (HIGH) | (IMPACT X PROBABILITY) Address highest first. | What can be done to lower or eliminate the impact or probability? | Who's responsible? | LEVEL
Delay in receiving transactional data from clients | Incomplete or delayed analysis and reporting | 5 | 3 | 15 | Regular follow-up procedures | Project Manager | 1
Data inaccuracies or inconsistencies in transactional records | Misleading or incorrect financial analysis | 5 | 3 | 15 | Implementing data validation checks,conduct regular data audits | Data Anlyst | 2
Technical issues with web application | Downtime to access analysis tools | 5 | 1 | 5 | Implement robust backup and recovery procedures, monitor system health | Developers | 3
Insufficient server capacity for data processing | slow performance or system crah | 3 | 3 | 9 | Monitor server load regularly,consider cloud-based solutions | IT Specialist | 4
Client confidentiality breaches | loss of client trust | 5 | 1 | 5 | Implement data encryption | Compilance team | 5

## Scale
RISK REGISTER SCALE
P R O B A B I L I T Y | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
I M P A C T